## Product Backlog
Vishal, Sahruday
Product Backlog
Unique ID | Task | Sprint | Estimated time (minutes) | Time after Iteration 1 | Time after Iteration 2 | Index | Information
Target Time
1 | Plan and Design | [5 empty] | Revised Target Time
1 | Create GitHub Repository | [5 empty] | Actual Time Taken
2 | Create Project Proposal | [5 empty] | New Task Added
2 | Implementation
2
Remaining effort
Total effort time
TDD Enactment
Task Code | Task Description

## Iteration backlog - 1
Group – 7: Abhishek Nalawade, Aditya Jadhav
Human Obstacle Detector
Iteration Backlog 1
Unique ID | Task | Target time (minutes) | Actual Time | Status | Completed
In Progress
1 | Plan and Design | 1390 | 1355 | Completed | To Do
1.11 | Create GitHub Repository | 10 | 10 | Completed
1.12 | Create Project Proposal | 320 | 380 | Completed
1.13 | Extensive Research on HOG, SVM and technology required | 360 | 375 | Completed
1.14 | Install Dependencies | 100 | 45 | Completed
1.15 | Check OpenCV installation working on Ubuntu | 30 | 30 | Completed
1.16 | Acquire Travis and Coveralls badges | 15 | 15 | Completed
1.17 | Add .travis.yml file with dependencies | 20 | 20 | Completed
1.18 | Add detailed Readme.md | 60 | 40 | Completed
1.19 | Create CmakeLists.txt file | 20 | 20 | Completed
1.2 | Update AIP Sheet | 50 | 75 | Completed
1.21 | Update Activity Diagram | 30 | 25 | Completed
1.22 | Update Readme and Quad-chart | 30 | 30 | Completed
1.23 | Git branching in the repository | 15 | 15 | Completed
1.24 | Test for Data Class | 25 | 20 | Completed
1.25 | Test for Detect Class | 25 | 25 | Completed
1.26 | Stub for Data Class | 30 | 30 | Completed
1.27 | Stub for Detect Class | 30 | 20 | Completed
1.28 | Stub for Distance Class | 20 | 20 | Completed
1.29 | Stub for Train Class | 20 | 20 | Completed
1.3 | Tests for Train Class and Distance Class | 20 | 40 | Completed
1.31 | Run Cpplint and Cppcheck | 60 | 40 | Completed
1.32 | Generate/Update Doxygen documentation | 60 | 20 | Completed
1.33 | Fill work log | 40 | 40 | Completed

## Iteration backlog - 2
Group – 7: Abhishek Nalawade, Aditya Jadhav
Human Obstacle Detector
Iteration Backlog 2
Unique ID | Task | Target time (minutes) | Actual Time | Status | Completed
In Progress
2 | Implementation | 1595 | 1515 | Completed | To Do
2.11 | Calibrate Camera Parameters | 40 | 40 | Completed
2.12 | Rework Class and Activity diagrams | 100 | 75 | Completed
2.13 | Implement getCamera() and loadVideo() of the Data class | 100 | 105 | Completed
2.14 | Write preprocessing() which is given to Detect class | 100 | 110 | Completed
2.15 | Update Data class tests | 45 | 30 | Completed
2.16 | Implement detectHuman() of the Detect class | 120 | 100 | Completed
2.17 | Implement putBox() to finish Detect class | 120 | 80 | Completed
2.18 | Update Detect class and its tests | 60 | 50 | Completed
2.19 | Update Main | 40 | 40 | Completed
2.2 | Update loadVideo() method in Data class | 50 | 50 | Completed
2.21 | Implement camToRobotTransform() and add findDepth() to Distance class | 100 | 115 | Completed
2.22 | Installing Eigen and updating CMakeLists | 30 | 30 | Completed
2.23 | Write displayLocation() in the Distance class | 100 | 85 | Completed
2.24 | Update Distance class tests | 60 | 60 | Completed
2.25 | Update all tests accordingly to increase coverage | 120 | 150 | Completed
2.26 | Re-run Cpplint and Cppcheck | 90 | 90 | Completed
2.27 | Update Class, Activity diagrams | 120 | 110 | Completed
2.28 | Update Readme.md | 80 | 80 | Completed
2.29 | Update Work log | 60 | 100 | Completed
2.3 | Update Doxygen documentation and results folder | 60 | 15 | Completed

## Work log
Group – 7: Abhishek Nalawade, Aditya Jadhav
Human Obstacle Detector
Work/Time log
Process Enactment |  | Pair Programming Roles |  |  |  |  | Interrupt
Task | Comment | Driver | Navigator | Date | Start | End | # | Time (mins) | Clean time
Iteration 1
github | Create GitHub repository | Aditya | Abhishek | 2021-10-05 | 16:25 PM | 16:35 PM | 0 | 0 | 10
projProp | Create Project Proposal | Both |  | 2021-10-07 | 14:40 PM | 20:00 PM | 2 | 60 | 380
openCV | Install OpenCV on Ubuntu 18.04 | Both |  | 2021-10-10 | 21:20 PM | 22:20 PM | 0 | 0 | 45
openCVtest | Test the OpenCV installation | Both |  | 2021-10-11 | 14:40 PM | 15:10 PM | 0 | 0 | 30
updateDocs | Update documentation such as UML, Activity diagrams, API sheet | Both |  | 10/13/2021 - 10/15/21 | 18:55 PM | 20:30 PM | 0 | 0 | 130
license | Add MIT License | Aditya | Abhishek | 2021-10-05 | 16:25 PM | 16:35 PM | 0 | 0 | 10
TravCover | Travis and Coveralls Updates | Aditya | Abhishek | 2021-10-15 | 19:40 PM | 20:00 PM | 0 | 0 | 15
workLog | Create/Update worklog | Aditya | Abhishek | 2021-10-14 | 19:30 PM | 20:00 PM | 0 | 0 | 30
stubData | Create a stub for Data class | Aditya | Abhishek | 2021-10-17 | 13:20 PM | 13:40 PM | 0 | 0 | 30
TestData | Creating tests for Data class | Aditya | Abhishek | 2021-10-18 | 13:40 PM | 14:00 PM | 0 | 0 | 20
stubDetect | Creating stub for Detect class | Aditya | Abhishek | 2021-10-17 | 17:15 PM | 17:35 PM | 0 | 0 | 20
TestDetect | Creating tests for Detect class | Aditya | Abhishek | 2021-10-17 | 17:35 PM | 17:50 PM | 1 | 5 | 25
initialTests | Write initial tests | Aditya | Abhishek | 2021-10-18 | 13:30 PM | 14:40 PM | 1 | 10 | 60
main | Altering main() | Aditya | Abhishek | 2021-10-17 | 22:20 PM | 22:35 PM | 0 | 0 | 15
stubTrain | Creating stub for Train class | Aditya | Abhishek | 2021-10-18 | 0:45 | 1:05 | 0 | 0 | 20
TrainTest | Creating tests for Train class | Aditya | Abhishek | 2021-10-18 | 1:05 | 1:25 | 0 | 0 | 20
stubDistance | Creating stub for Distance class | Aditya | Abhishek | 2021-10-18 | 1:25 | 1:45 | 0 | 0 | 20
TestDistance | Creating tests for Distance class | Aditya | Abhishek | 2021-10-18 | 1:45 | 2:05 | 0 | 0 | 20
writeData | Adding methods to Data class | Aditya | Abhishek | 2021-10-17 | 21:25 PM | 22:45 PM | 0 | 0 | 80
writeDetect | Adding methods to Detect class | Aditya | Abhishek | 2021-10-17 | 22:45 PM | 0:35 | 1 | 10 | 110
readme | Updates in README | Aditya | Abhishek | 2021-10-18 | 8:00 | 8:15 | 0 | 0 | 15
Cpp11 | Adopting C++ 11,14 features into code | Aditya | Abhishek | 2021-10-17 | 22:35 PM | 22:55 PM | 0 | 0 | 20
Doxygen | Add Doxygen files | Aditya | Abhishek | 2021-10-18 | 10:00 | 10:10 | 0 | 0 | 10
workLog | Update worklog | Both |  | 2021-10-18 | 11:45 | 12:15 | 0 | 0 | 30
Iteration 2
updateDocs | Updates in Activity, Class diagrams and AIP Sheet | Both |  | 2021-10-20 | 20:00 PM | 21:15 PM | 0 | 0 | 75
UMLact | UML activity diagram changes | Both |  | 2021-10-21 | 14:40 PM | 15:10 PM | 0 | 0 | 30
UMLcls | UML class diagram changes | Both |  | 2021-10-21 | 15:10 PM | 15:30 PM | 0 | 0 | 20
writeDetect | Adding methods to Data class | Abhishek | Aditya | 2021-10-23 | 17:15 PM | 19:05 PM | 1 | 5 | 105
newMembers | Add new function or data members wherever required | Abhishek | Aditya | 2021-10-24 | 8:15 | 10:25 | 0 | 0 | 130
writeDistance | Adding methods to Distance class | Abhishek | Aditya | 2021-10-24 | 10:25 | 11:50 | 1 | 5 | 85
main | Altering main | Abhishek | Aditya | 2021-10-24 | 11:50 | 12:30 | 0 | 0 | 40
writeData | Adding methods to Data class | Abhishek | Aditya | 2021-10-24 | 12:30 | 13:20 | 0 | 0 | 50
writeDetect | Adding methods to Detect class | Abhishek | Aditya | 2021-10-24 | 13:20 | 15:30 | 1 | 10 | 130
InstallEigen | Installing Eigen Library | Abhishek | Aditya | 2021-10-24 | 15:30 | 16:00 | 0 | 0 | 30
newMembers | Add new function or data members wherever required | Abhishek | Aditya | 2021-10-24 | 16:00 | 17:00 | 0 | 0 | 60
updateTests | Update unit tests | Abhishek | Aditya | 2021-10-24 | 17:00 | 19:30 | 3 | 50 | 150
IncCov | Increasing coverage by adding tests | Abhishek | Aditya | 2021-10-24 | 19:30 | 20:40 | 0 | 0 | 100
OptCode | Code Optimization using cppcheck, cpplint | Abhishek | Aditya | 2021-10-24 | 20:40 | 22:10 | 0 | 0 | 90
readme | Updates in README | Abhishek | Aditya | 2021-10-25 | 2:05 | 3:25 | 0 | 0 | 80
Cpp11 | Adopting C++ 11,14 features into code | Abhishek | Aditya | 2021-10-25 | 3:25 | 3:45 | 0 | 0 | 20
Doxygen | Update Doxygen files | Abhishek | Aditya | 2021-10-25 | 3:45 | 4:00 | 0 | 0 | 15
workLog | Update worklog | Both |  | 2021-10-25 | 4:00 | 5:40 | 2 | 40 | 100